## V-Cycle
Planning and SW Requirement Analysis
SW Design
Module Verification
SW Validation
Implementation
SW Verification and Validation Plan

## Requirement Analysis
Requirements Analysis
Propouse | Identify and Analyze SW Requirements
Entry Criteria | -Problem Description
- Traceability Matrix Template
- Design especification Document Template
- Test Plan template
Step | Activities | Description
1 | Requirements Engineering | Identify the functional and non-functional SW component requirements |  | X
Collect requirements into the Traceability Matrix Tool ( requirements Section)
|  | Ensure that the requirements statement is clear and unambiguous. | X | X
Review the requirements with their stakeholders and Resolve any questions.
2 | Planning -Estimation | Porduce a Conceptual design base on the requirements (Block Diagram, Boundary Diagram)
Document the Conceptual desing into the Design Especification Document
Based on the modules defined,Estimate the effort required to develop each of those modules
Create a schedule plan to implement System
3 | Test Planning | Specify tests procedures for high level requirement validation
For each of the requirements defined, specify the test acceptance criteria
Document the test procedures into the test plan template
Include the test specifications into the Traceability Matrix Template (testing Section)
Exit Criteria | - Traceability Matrix filled out with the requirements well defined and categorized
- Plan to implement the changes
- Conceptual design into the Design specification Document
- Test procedures for requirements verification
- Checked in all working documents into the repository
'Back to V-Cycle

## SW Design
Software Design
Propouse | Review the requirements and produce a design specification to meet them.
Entry Criteria | - Requirement Specifications from the Traceability Matrix Template
- Conseptual design
- Design Specification template
- Design Review Check List
- Defect recording Logs template
Step | Activities | Description
1 | Module Design | - Review the requirements and produce an external Desing specification to meet them.
- Document the Desing using the DSD Document
update the traceability matrix (Design Section ) with the desing information
- Record in the Defect Recording log any requirements defects found.
2 | Module Test Verification | - Base on the design module definition, create test procedure to verify the module functionality
- Use Test plan template to Document Test cases
Exit Criteria | - Completed Traceability Matrix Template (Design Section )
- Completed Design Specification template
- Completed defect Recording log
- Checked in all working documents into the repository
'Back to V-Cycle

## Implementation
Implementation
Propouse | Implement the Code following the Coding standards
Hector Cuellar
Entry Criteria | - Design Specification
- Traceability Matrix Template
- Code Review Check List
-Naming Convention
- Defect Log Template
Step | Activities | Description
1 | Code | Implement the code Following the Naming and coding estandar
Record in the Defect Recording log any requirements or design defects found.
update the traceability matrix (Coding Section ) with the Code information
2 | Code Review | Follow the Code Review checklist and review the code.
Identify and clasify any issue found
Fix all defects found (coming from design or requirements)
3 | Compile | Compile the program until there are no compile errors.
Fix all defects found
Record defects in the Defect Recording log.
Exit Criteria | - program compliled sucessfully
- Completed Code Review Check List
- Traceability Matrix Template
- Checked in all working documents into the repository
'Back to V-Cycle

## Module Verification
Module Verification
Propouse | Validate SW design using test procedures
Entry Criteria | - Test Plan
- SW Compliled
- Defect Log Template
Step | Activities | Description
1 | Test Verification | - Review the test cases previously defined and make any update as needed
i.e. add a missing test case for a certain functionality
- update the respective test plan document
2 | Test Execution | - Run each of the test cases until all tests run without error.
- Record defects in the Defect Recording log.
- Fix all defects found ( if the defect comes from previous phases like design or requirements, update the respective documents (DSD, C Code files, test plan ))
Exit Criteria | - A thoroughly tested modules
- Completed Test Report template
- Completed Defect Recording logs
- Checked in all working documents into the repository
'Back to V-Cycle

## SW Validation
SW Validation
Propouse | validate that the SW meet the requirements
Entry Criteria | - Test Plan
- SW Compliled and tested
- Defect Log Template
Step | Activities | Description
1 | Test Verification | - Review the test cases previously defined and make any update as needed
i.e. add a missing test case for a certain Requirement
- update the respective test plan document
2 | Test Execution | - Run each of the test cases until all tests run without error.
- Record defects in the Defect Recording log.
- Fix all defects found , if the defect comes from previous phases like design or requirements, update the respective documents (DSD, C Code files, test plan ))
Exit Criteria | - A thoroughly tested program
- Completed Test Report template
- Requirement Traceability Matrix Template
- Completed defect Recording logs
- Checked in all working documents into the repository
| Final Analysis | Review the defect log to verify that all of the defects found in each phase were recorded.
Using your best recollection, record any omitted defects.
Analyze the defect log. Identify which are the most common and critical defects. In which phases were introduced the most number of defects.
Based on your analysis Consider to include/update some of those topics into the reviews checklist and test plans for further development
'Back to V-Cycle
'Back to V-Cycle